## Product Backlog
Product Name: | Library Management System
Name: | Atafo Abure
Initials: | AA
Student ID: | 1001442575
Total Features | Left | Available | Completed | Sprint Ends
Start | 28 | 28 | 0
Sprint 1 | 24 | 28 | 4 | 2018-03-30
Sprint 2 | 18 | 28 | 10 | 2018-04-08
Sprint 3 | 15 | 28 | 13 | 2018-04-15
Sprint 4 | 9 | 28 | 19 | 2018-04-22
Sprint 5 | 6 | 28 | 22 | 2018-04-29
Note: Priority of unfinished Features is subject to change at the end of each sprint at the whim of the Product Owner
Additional features may be proposed by the student / team but must be approved by the Product Owner in writing
Feature ID | Priority | Status | Expected Sprint | Actual Sprint # | As a … | I want to… | So that… | Type | Notes
CM | 1 | COM | 1 | 1 | PM | Create any type of media | I can check out media and create bundles | CLI | No Menu Required
CBN | 2 | COM | 1 | 1 | PM | Create a bundle of media | I can check out bundles | CLI | No Menu Required
CLR | 3 | COM | 1 | 1 | PM | Create a Librarian | They can check out/in media | CLI | No Menu Required
CC | 4 | COM | 1 | 1 | LB | Create a Customer | We can keep track of who has what media | CLI | No Menu Required
| 5 | COM | 2 | 2 | CU | Browse Catalog | they can see what is available | CLI | Need to list all media. Also list all bundles and media in those bundles. Creating Menu
| 6 | COM | 2 | 2 | PM | Add or Create | I can do it from a menu | CLI | Requires MVC
| 7 | COM | 2 | 2 | LB | Check out Media | Customers can check out books | CLI | Librarian creates transaction with customer info | Need to fix check in and check out for transaction
| 8 | COM | 2 | 2 | LB | Check in Media | Customers can check in books | CLI | Librarian modifies transaction to check in
| 9 | COM | 2 | 2 | CU | Pay Balance | Pay fine and check out new books | CLI | Customer can't check out media till balance is paid
| 10 | COM | 2 | 2 | PM | Save/Load Data | Don’t loose records of clients, media, and transaction | CLI | Should be options in the menu
| 11 | COM | 3 | 3 | ALL | Open a main GUI Window | I can use my mouse | GUI | Just opening a window
| 12 | COM | 3 | 3 | PM | Create Media and Bundles Via GUI | Make this process more user friendly | GUI | Be able to do this in dialog windows
| 13 | COM | 3 | 3 | CU | Browse GUI Catalog | They can see what is available | GUI | Dialog Windows
| 14 | COM | 4 | 4 | PM | Create Librarians via GUI | They can check out/in media | GUI | Same as before but in a GUI
| 15 | COM | 4 | 4 | LB | Create Customers via aGUI | We can keep track of who has what media | GUI | Same as before but in a GUI
| 16 | COM | 4 | 4 | LB | Check out Media in GUI | Customers can check out books | GUI | Same as before but in a GUI
| 17 | COM | 4 | 4 | LB | Check in Media in GUI | Customers can check in books | GUI | Same as before but in a GUI
| 18 | COM | 4 | 4 | CU | Pay Balance in GUI | Pay fine and check out new books | GUI | Same as before but in a GUI
| 19 | COM | 4 | 4 | ALL | See a menu Bar | Make it easier to find stuff | GUI | Still have dialog boxes, but main menu dialog box is replaced with menu bar
| 20 | COM | 5 |  | PM | See everything that’s checked out and to who | See what's not in the library | GUI | A scrollable list
| 21 | COM | 5 |  | PM | Save/Load Data to default file name | Don’t loose records of clients, media, and transaction | GUI | Save to whatever file was opened, or a defualt name
| 22 | COM | 5 |  | PM | Save and Load from different file names | Manage multiple libraries | GUI | Save/load to a user specified file
| 23 | NS | 6 |  | CU | See pictures of the media | So customers can see what book to look for | GUI | Picture must be added when creating media
| 24 | NS | 6 |  | ALL | Have users log in | So not all options are available to everyone | GUI | Can be hardcoded user names and passwords, such as "PM" for project manager with password "password". Each user type must have different usernames and passwords
| 25 | NS | 6 |  | LB | Bulk Check Out/In | So that librarians can check out multiple books at once | GUI | One window where multiple media ids can be typed, and check out multiple customers at once
| 26 | NS | 7 |  | ALL | Undo | Undo mistakes | GUI | Undo events (add media, check out, etc)
| 27 | NS | 7 |  | ALL | Copy Paste | Not waste time typing | GUI | Just do it where you can. It's built in some places. Don't start your own.
| 28 | NS | 7 |  | ALL | Have this in one window | It's not full of pop up dialog boxes | GUI | All contents in a window. Different window layout for different users

## Sprint 1
Sprint # | 1
Start on | 2018-03-24
End on | 2018-03-30
Total Tasks | 30
Day 1 Left | 30
Day 2 Left | 9
Day 3 Left | 0
Day 4 Left | 0
Day 5 Left | 0
Day 6 Left | 0
Day 7 Left | 0
Task ID | Feature ID | Category | Type | Assigned To | Description | Status | Notes
1 | CM | Architecture | UML | AA | Add methods to Media and derived classes | COM - Completed
2 | CM | Media | Code | AA | Write and compile empty Media class | COM - Completed
3 | CM | Media | Code | AA | Variables and Constructor | COM - Completed
4 | CM | Media | Code | AA | Operator Overload << | COM - Completed
5 | CM | Media | Test | AA | Test Constructor and << | COM - Completed
6 | CM | Media | Code | AA | Add Get Methods | COM - Completed
7 | CM | Wrap Up | UML | AA | Update UML to match new methods if changed | COM - Completed
8 | CM | Media | Test | AA | Test get methods in main | COM - Completed
9 | CB | Architecture | UML | AA | Add methods to Bundle and derived classes | COM - Completed
10 | CB | Bundle | Code | AA | Write and compile empty Bundle class | COM - Completed
11 | CB | Bundle | Code | AA | Variables and Constructor | COM - Completed
12 | CB | Bundle | Code | AA | Operator Overload << | COM - Completed
13 | CB | Bundle | Test | AA | Test Constructor and << | COM - Completed
14 | CB | Bundle | Code | AA | Add Get Methods | COM - Completed
15 | CB | Bundle | Test | AA | Test get methods in main | COM - Completed
16 | CL | Architecture | UML | AA | Add methods to Librarian | COM - Completed
17 | CL | Librarian | Code | AA | Write and compile empty Librarian class | COM - Completed
18 | CL | Librarian | Code | AA | Variables and Constructor | COM - Completed
19 | CL | Librarian | Code | AA | Operator Overload << | COM - Completed
20 | CL | Librarian | Test | AA | Test Constructor and << | COM - Completed
21 | CL | Librarian | Code | AA | Add Get Methods | COM - Completed
22 | CL | Librarian | Test | AA | Test get methods in main | COM - Completed
23 | CC | Architecture | UML | AA | Add methods to Customer | COM - Completed
24 | CC | Customer | Code | AA | Write and compile empty Customer class | COM - Completed
25 | CC | Customer | Code | AA | Variables and Constructor | COM - Completed
26 | CC | Customer | Code | AA | Operator Overload << | COM - Completed
27 | CC | Customer | Test | AA | Test Constructor and << | COM - Completed
28 | CC | Customer | Code | AA | Add Get Methods | COM - Completed
29 | CC | Customer | Test | AA | Test get methods in main | COM - Completed
30 | Demo | Wrap Up | Delivery | AA | Zip up and deliver sprint #1 (UML, Code, and spreadsheet) | COM - Completed | Zip up code, uml and scrum spreadsheet

## Sprint 2
Sprint # | 2
Start on | 2018-04-02
End on | 2018-04-08
Total Tasks | 31
Day 1 Left | 25
Day 2 Left | 20
Day 3 Left | 11
Day 4 Left | 7
Day 5 Left | 3
Day 6 Left | 0
Day 7 Left | 0
Task ID | Feature ID | Category | Type | Assigned To | Description | Status | Notes
1 | CL | Architecture | UML | AA | Add Methods to Library and Derived classes | COM
2 | CL | Library | Code | AA | Write and compile empty Library class | COM
3 | CL | Library | Code | AA | Variables and Constructor | COM
4 | CL | Library | Code | AA | Operator Overload << | COM
5 | CL | Library | Test | AA | Test Constructor and << | COM
6 | CL | Library | Code | AA | Add Get Methods | COM
7 | CL | Wrap Up | UML | AA | Update UML to match new methods if changed | COM
8 | CT | Architecture | UML | AA | Add Methods to Transaction and Derived classes | COM
9 | CT | Transaction | Code | AA | Write and compile empty Transaction class | COM
10 | CT | Transaction | Code | AA | Variables and Constructor | COM
11 | CT | Transaction | Code | AA | Operator Overload << | COM
12 | CT | Transaction | Test | AA | Test Constructor and << | COM
13 | CT | Transaction | Code | AA | Add Get Methods | COM
14 | CT | Wrap Up | UML | AA | Update UML to match new methods if changed | COM
15 | CD | Architecture | UML | AA | Add Methods to Date and Derived classes | COM
16 | CD | Date | Code | AA | Write and compile empty Date class | COM
17 | CD | Date | Code | AA | Variables and Constructor | COM
18 | CD | Date | Code | AA | Operator Overload << | COM
19 | CD | Date | Test | AA | Test Constructor and << | COM
20 | CD | Date | Code | AA | Add Get Methods | COM
21 | CD | Wrap Up | UML | AA | Update UML to match new methods if changed | COM
22 | CV | View | Code | AA | Create menu propmts in view | COM
23 | CV | View | Code | AA | Write and compile empty View | COM
24 | CV | View | Code | AA | Test Meun prompts in view | COM
25 | CV | Wrap Up | UML | AA | Update UML to match new methods if changed | COM
26 | CC | Controller | Code | AA | Create Controller to implement MVC | COM
27 | CC | Controller | Code | AA | Write and compile empty Controller | COM
28 | CC | Controller | Code | AA | Test MVC | COM
29 | CC | Controller | Code | AA | Test Save and Load functionality | COM
30 | CC | Wrap Up | UML | AA | Update UML to match new methods if changed | COM
31 | Demo | Wrap Up | Delivery | AA | Zip up and deliver sprint #2 (UML, Code, and spreadsheet) | COM | Zip up code, uml and scrum spreadsheet

## Sprint 3
Sprint # | 3
Start on | 2018-04-09
End on | 2018-04-15
Total Tasks | 5
Day 1 Left | 5
Day 2 Left | 5
Day 3 Left | 5
Day 4 Left | 5
Day 5 Left | 5
Day 6 Left | 0
Day 7 Left | 0
Task ID | Feature ID | Category | Type | Assigned To | Description | Status | Notes
1 | CD | GUI | Code | AA | Allow GUI to interact with current classes | COM
2 | CD | GUI | Code | AA | Allow customers to see main window | COM
3 | CD | GUI | Code | AA | Allow GUI selection of different menu items | COM
4 | CD | GUI | Code | AA | Prints out all media in a dialog box | COM
5 | Demo | Wrap Up | Delivery | AA | Zip up and deliver sprint #3 (UML, Code, and spreadsheet) | COM | Zip up code, uml and scrum spreadsheet

## Sprint 4
Sprint # | 4
Start on | 2018-04-16
End on | 2018-04-22
Total Tasks | 14
Day 1 Left | 14
Day 2 Left | 14
Day 3 Left | 14
Day 4 Left | 14
Day 5 Left | 14
Day 6 Left | 5
Day 7 Left | 0
Task ID | Feature ID | Category | Type | Assigned To | Description | Status | Notes
1 | MM | GUI | Code | AA | Allow Librarians to be created via GUI | COM
2 | MM | GUI | Test | AA | Test if Librarians can be created via GUI | COM
3 | MM | GUI | Code | AA | Allow Customers to be created via GUI | COM
4 | MM | GUI | Test | AA | Test if Customers can be created via GUI | COM
5 | MM | GUI | Code | AA | Allow Customers to check in media via GUI | COM
6 | MM | GUI | Test | AA | Test if check in can be done via GUI | COM
7 | MM | GUI | Code | AA | Allows Customers to check out media via GUI | COM
8 | MM | GUI | Test | AA | Test if check out can be done via GUI | COM
9 | MM | GUI | Code | AA | Allows Customers to pay a balance via GUI | COM
10 | MM | GUI | Test | AA | Test if pay balance can be done via GUI | COM
11 | MM | GUI | Code | AA | Allow the Library Manament system to utilize a menu bar for various functions | COM
12 | MM | GUI | Test | AA | Test Menu bar | COM
13 | MM | GUI | UML | AA | Update UML to match new methods if changed | COM
14 | Demo | Wrap Up | Delivery | AA | Zip up and deliver sprint #4 (UML, Code, and spreadsheet) | COM | Zip up code, uml and scrum spreadsheet

## Sprint 5
Sprint # | 5
Start on | 2018-04-23
End on | 2018-04-29
Total Tasks | 7
Day 1 Left | 7
Day 2 Left | 7
Day 3 Left | 7
Day 4 Left | 7
Day 5 Left | 7
Day 6 Left | 6
Day 7 Left | 0
Task ID | Feature ID | Category | Type | Assigned To | Description | Status | Notes
1 | CL | Library | Code | AA | Allow users to see current stock levels | COM
2 | MM | GUI | Code | AA | Implememt save functionality | COM
3 | MM | GUI | Test | AA | Test Save Functionality | COM
4 | MM | GUI | Code | AA | Implement Load Functionality | COM
5 | MM | GUI | Test | AA | Test Load Functionality | NS
6 | MM | GUI | UML | AA | Update UML to match new methods if changed | COM
7 | Demo | Wrap Up | Delivery | AA | Zip up and deliver sprint #5 (UML, Code, and spreadsheet) | COM | Zip up code, uml and scrum spreadsheet